## Sheet1
Smart Alarm Clock
Royal University of Phnom Penh |  |  | Faculty of Engineering
Deadline: 4/30/2023
| Action | Responsible | Start Date | End Date
Week #1: Researching
| ESP32 Module | Sreynen | 2023-02-20 | 2023-02-22
| Thunkable + Text to speech | Soriya | 2023-02-20 | 2023-02-24
| 7 segment 4 digit ft speaker | Sreynen | 2023-02-23 | 2023-02-25
| Discussing | Group | 2023-02-26 | 2023-02-27
Week #2&3: Hardware
| ESP32 Module ft 7 segment | Soriya | 2023-02-28 | 2023-03-14
| ESP32 Module ft speaker | Sreynen | 2023-02-28 | 2023-03-14
| Discussing | Group | 2023-03-15 | 2023-03-16
Week #4&5: Software
| Thunkable + Text to speech | Soriya | 2023-03-17 | 2023-03-29
| ARDUINO IDE | Sreynen | 2023-03-17 | 2023-03-29
| Discussing | Group | 2023-03-30 | 2023-03-31
Week #6&7: Software and Hardware testing
| ARDUINO IDE+ESP32 Module + 7 segment | Soriya | 2023-04-02 | 2023-04-06
| ARDUINO IDE +ESP32 Module + speaker | Sreynen | 2023-04-02 | 2023-04-06
| ARDUINO IDE+ESP32 Module + 7 segment + speaker | Group | 2023-04-08 | 2023-04-11
| Discussing | Group | 2023-04-13 | 2023-04-14
Week #8&9: Retesting &3D Print
| Retesting | Group | 2023-04-16 | 2023-04-18
| 3D Printing clock case and retesting | Group | 2023-04-20 | 2023-04-28
| Discussing | Group | 2023-04-29 | 2023-04-30